## Slide 1
April, 2020
Executive Director Report

## Slide 2
Current Status
Campaign Position – STABLE
  Positive momentum built
  Construction Docs Begun
  Renderings and Fly Through nearing finalization
  Over $5.8MM in Capital Escrow Account
Operational Position – STABLE
  Increased social media position
  Increased content library
  Stable financial picture – expenses covered through end of June
  Community engagement programming continuing

## Slide 3
Unknowns
Campaign
  Impact to campaign timeline?
  Impact to construction timeline?

## Slide 4
PROGRAM! PROGRAM! PROGRAM!
Making Waves Digital Show
Community Engagement Pivot
  New partnerships with local Non-Profit Health & Human Services Organization to create Arts & Culture Wish Lists
    Ada Jenkins Center
    Children’s Hope Alliance

## Slide 5
April, 2020 Campaign Report

## Slide 6
March Pledge Activity
15 new pledges totaling $73,665 on a $100,000 goal
Total pledges equal $10,169,765
Total fundraising, including land and bond, equals $15,669,765
This total does not include verbal pledge of $250,000 from Aquesta Bank

## Slide 8
March Cash Activity
23 payments totaling $67,546 on a goal of $37,816

## Slide 10
RECOMMENDATION
Delay Public Phase fundraising for some period of time
  Continue focus on major gifts
  Continue to seek grants
  Stay in front of donors with positive news and programs

## Slide 11: Original Plan
December 31, 2020 Campaign fully pledged
February 1, 2021 Bidding begins
April 1, 2021 Construction begins
June, 2022 Construction complete
September, 2022 First season begins

## Slide 12: New Scenario 3- Month Public Phase Delay July 1, 2020 Resume
No capital fundraising takes place April 1 – June 30
Use time to support partners, communicate, execute projects, plan
July 1 house parties resume
In person gala takes place 9/12/20
Brick campaign kicks off at gala
Public phase kicks off 10/1/20
Community events resume

## Slide 13: New Scenario Timeline July 1, 2020 Resume
April 31, 2021 Campaign fully pledged
May 1, 2021 Bidding begins
July, 2021 Construction begins
October, 2022 Construction complete
December, 2022 Soft open
Fall, 2023 First full season begins

## Slide 14
CCA – Covid-19 Scenarios
2020
2022
FUNDRAISING
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
SEP
PUBLIC CAMPAIGN
Original
2021
CONSTRUCTION & OPENING
Construction & Move In
OPERATIONS
CD’S
CAC RAMP
OCT
NOV
DEC
JAN
BID
FEB
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
PUBLIC CAMPAIGN
2023
Ramp
Scenario 1
Original
Scenario 1
CD’S
BID
SOFT
SEASON 1
SEASON 2
SOFT
SEASON 1
1/2 SEASON
ANNUAL FUND / ENDOWENT
ANNUAL FUND / ENDOWMENT
Construction & Move In
CAC SOFT
CAC YEAR 1
CAC
Staff
TD
BO & OTHERS
TD
BO & OTHERS
Scenario 1
PM
PM
Quiet