## Construction BvA Summary
Cain Center | Spent Thru | Projected | Projected | Approved | Projected
Budget vs. Projection | 2021-09-09 | to be Spent | Budget | Budget | Variance
Professional Services | 1801559.71 | 570566.29 | 2372126 | 2282931 | -89195
Architectural | 1744023.94 | 438907.06 | 2182931 | 2182931
Other Professional Services | 57535.77 | 131659.23 | 189195 | 100000
Fundraising | 600000 | 0 | 600000 | 600000 | 0 | *transferred to operating
Construction | 851962.63 | 17738579.031 | 18568580.401 | 18593835.85 | 25255.449
Pre-Construction(Rodgers) | 45000 | 0 | 45000 | 45000
Contract (Edifice) | 755622.63 | 15329156.37 | 16062817.74 | 16084779
Contingency (15%) | 0 | 2409422.661 | 2409422.661 | 2412716.85
Permitting | 51340 | 0 | 51340 | 51340
Financing | 56187.5 | 43812.5 | 100000 | 100000 | 0
Owner Held Items | 377 | 840227 | 840604 | 600000 | -240604
Land | 1500000 | 0 | 1500000 | 1500000 | 0
Sales Tax Reimbursement | 0 | -320000 | -320000 | -320000 | 0
Total | 4810086.84 | 18873184.821 | 23661310.401 | 23356766.85 | -304543.551 | *to come out of contingency
Last Update: | 9.13.21
Funding Sources:
Cash in Bank | 8809820.05 | 9.13 Bank Account Online
Cash Spent | 3310086.84 | Un-Reconciled
Pledge Receivables | 1784286.46 | 8.31 Balance Sheet
County Funds Committed | 1500000 | 8.31 Balance Sheet
Town Funds Committed | 4000000 | 8.31 Balance Sheet
State Funds (Potential) | 2500000
Value of Land | 1500000
Income (future pledges) | 1775610 | Un-Reconciled
Total | 25179803.35
Less: Projected Budget | -23661310.401
Potential Initial Capital Endowment | 1518492.949 | *if spend 100% of contingency