Oct 17-21

* Install A/V
* Catwalk and grid lighting installation
* Building systems commissioning
* Install Fabric Wrapped Panels

Oct 24-28

* Install A/V
* Install Performance Hall Floor
* Order all equipment for Cain Center for the Arts

Oct 31-Nov 4

* Install A/V
* Install Performance Hall seating

Nov 7-11

* Install Performance Hall lighting

Nov 15-21 (Building TCO)

* A/V Commissioning
* Test/ Training AV
* Spectrum to complete phone/internet installation

Nov 21-25

* Soft-goods and theatre Drapery install
* Cintas to install TP, Soap, Paper Towel dispensers

Nov 28- Dec 2

* Deadline- Internet/phones need to work at Cain Center
* CCP to assist with computer transition and installation
* Washer/ Dryer/Fridge delivery/installation
* Thomas Icemaker/fridge Delivery/installation
* Theatrical Commissioning
* Shelving installation for closets (if possible)
* Deadline- Receive all Audio, Lighting, and assorted equipment
* Studio design gallery installation

**Dec 5 – Dec 9**

* Cain Center Office Furniture delivery
* Build tech closet storage.
* Shelving installation for closets
* Acoustical Commissioning - building to be quiet/vacant, confirm time over weekend

**Dec 12 – Dec 16**

* CAC Office moves out and into Cain Center
* Gallery installation, hallway wall installation, classroom installation
* Volunteer and Staff Training
* Dry Run for Ticketing/backstage crews
* Test run all Performance Hall equipment with a live Band
* Setup Board Room, Classrooms, dressing rooms
* Event/band to test Performance Hall equipment

**Dec 19 – Dec 23**

* Final Punch List items
* Final setup and testing
* Final cleaning of space

**Dec 27- Dec 30**

* **Be ready to open the building**

**January:**

**Jan 3 Open House**

**Jan 5-6 Ribbon Cutting**

**Jan 8 Big Concert**

**Jan 14 Christian Sands**

**Jan 21 Forever Young**